## As per Invoice
As per Invoice
Invoice Number | Invoice Date | Vendor | Invoice Description | Quantity | Taxable Value | GST | Invoice Amount | Difference Amount | PO Number
FP/25-26/259 | 14-Jul-25 | Freezing Point | Supply of AHU-101 (18TR/20HP), AHU-103/104 (25TR/32HP), AHU-113 (35TR/44HP), AHU-114 (25TR/32HP) in multiple modules w/ expansion valve to suit DX coil circuits - RA-1 Supply 70% against material delivery at site | 2.80 NOS | 3080368.9 | 862503.26 | 3942872 | -0.16 | 100066093
FP/25-26/280 | 25-Jul-25 | Freezing Point | Supply of AHU-107 (38TR/48HP), AHU-112 (38TR/48HP) in multiple modules w/ expansion valve to suit DX coil circuits - RA-2 Supply 70% against material delivery at site | 1.40 NOS | 2222694.6 | 622354.48 | 2845049 | -0.08 | 100066093
FP/25-26/395 | 11-Sep-25 | Freezing Point | Supply of Air Handling Units - DX cooling coil, AHU-101/103/104/107/112/113/114 - RA-4 Supply 70% against material delivery at site | 4.20 NOS | 1901635.4 | 532457.88 | 2434093 | -0.28 | 100066093
FP/25-26/444 | 17-Oct-25 | Freezing Point | Supply of AHU-103/104, AHU-105/106, AHU-116/117, AHU-109 in multiple modules; copper pipes, tube insulation, cabling, MS support structure - RA-5 Supply 70% against material delivery at site | See invoice (NOS/MTR/KG mix) | 8219461.5 | 1479503.04 | 9698965 | 0.46 | 100066093
FP/25-26/453 | 25-Oct-25 | Freezing Point | Supply of Air Handling Units - DX cooling coil, AHU-103/104, AHU-105/106, AHU-116/117, AHU-109 - RA-6 Supply 70% against material delivery at site | 4.20 NOS | 3721040.4 | 669787.28 | 4390828 | 0.32 | 100066093
FP/25-26/468 | 06-Nov-25 | Freezing Point | Supply of AHU DX cooling coils, VRV ODU units (AHU-103/104,105/106,116/117,109), BMS BACnet card, copper pipes, tube insulation, cabling, cable tray, MS support structure, tube frame - RA-8 Supply 30% against material delivery | See invoice (NOS/MTR/KG mix) | 6980747.1 | 1256534.5 | 8237281 | -0.6 | 100066093
FP/25-26/477 | 08-Nov-25 | Freezing Point | Providing VRF System for Phase-4 AHU at JFWTC - Installation Work (Details as per Annexure) - RA-09 Installation | 1.00 NOS | 1010580 | 181904.4 | 1192484 | -0.4 | 100066093
FP/25-26/535 | 29-Nov-25 | Freezing Point | Supply of copper pipes, tube insulation, cabling, cable tray with cover - RA-10 Supply | See invoice (MTR/RMT mix) | 1738908 | 313003.44 | 2051911 | -0.44 | 100066093
|  |  | Total |  | 28875435.9 | 5918048.28 | 34793483 | -1.18